August 2026 — How-To

Month 3: Transfer stress test and initial writing

Goal for the month: run the pre-registered transfer experiment as a stress test of signal portability (not a generalization claim); analyze results against baselines; begin drafting the methodologically argued sections; end the summer with a defensible interim chapter draft, even if some sections (esp. UQ and discussion) remain incomplete. A weak or null transfer outcome is a publishable boundary result — plan for that outcome as well as a positive one.

# Prerequisites from July

- All three detectors fitted on Kerkrade with anomaly scores/flags.

- Four-part evaluation protocol run on Kerkrade with results.

- SMAP and API baselines computed.

- Transfer sites ingested (at least 3).

- Transfer experiment pre-registered.

# Week 1 (August 1-7): Transfer stress test — execution

## Task 1.1 — Train transfer-ready model(s) at Kerkrade

- Why — The transfer model deploys what was learned at Kerkrade to other sites. The training procedure has to be defined precisely so it can run at sites that lack CO2 sensors.

- How — Recommended specification: at Kerkrade, train each of the three detectors on the *non-CO2* feature set only (weather + pressure tendency + PM if available at transfer sites). This is the configuration that can be deployed at sites without CO2. The Kerkrade CO2 is the training label proxy — anomalous CO2 windows are the positives. Note: this is now a supervised or semi-supervised setup; reconcile with the unsupervised IF / Kalman framing in the methods chapter.

- Output — Three trained-transfer models: sarimax-transfer.pkl, kalman-transfer.pkl, iforest-transfer.pkl. Documented training procedure.

- Time — 1-2 days.

## Task 1.2 — Deploy at each transfer site

- How — For each transfer site (Maastricht, Roermond, Liège, Aachen, Charleville-Mézières or whichever subset is in hand): feed the site's non-CO2 features through each trained transfer model. Output an anomaly score time series for each (site, model) pair.

- Output — data/processed/transfer-anomalies/{site}-{model}.csv. Plot of anomaly scores per site.

- Time — 1 day.

## Task 1.3 — Build per-site soft labels

- Why — Need labels at each transfer site to evaluate against. Same soft-label methodology as Kerkrade (discharge percentile).

- How — For each transfer site, identify the nearest discharge gauge with continuous Jan 2025-present data. Mark ≥90th and ≥95th percentile events. Define antecedent windows.

- Output — data/processed/events-{site}.csv per site.

- Time — 1 day total across sites.

# Week 2 (August 8-14): Transfer results analysis

## Task 2.1 — Run pre-registered evaluation at each site

- How — Apply the same four-part protocol from July to each transfer site's anomaly scores. Report results per site per detector.

- Output — Script 11_transfer_evaluation.py. Results table: site × detector × protocol.

- Time — 2 days.

## Task 2.2 — Baseline comparison

- Why — Section 13.5 requirement: the transfer signal must beat API and SMAP at the transfer sites to count as contribution. Otherwise the result is still publishable but with a narrower claim.

- How — For each transfer site, compute API and SMAP anomaly scores using the same ≥90th-percentile windows. Compare to the transferred IoT-derived anomaly scores via the same statistical test from the pre-registration.

- Output — Results table: site × {transferred IoT signal vs. API vs. SMAP}. Plot of comparative performance.

- Time — 1 day.

## Task 2.3 — Honest read of the results

- Why — Before writing, look at what actually happened. Don't pre-cook the narrative.

- How — Three possible outcomes: (A) transferred IoT beats API/SMAP at most sites — the headline result. (B) transferred IoT comparable to API/SMAP — useful, narrower. (C) transferred IoT underperforms API/SMAP — null result, still publishable with proper analysis. Identify which outcome you have. If (A) or (B), the chapter is on track. If (C), the discussion section becomes more important; the chapter then tells the story of why low-cost IoT didn't beat satellite/rainfall-derived proxies in this regime.

- Output — Updated decisions log entry summarizing the outcome and its implications for the chapter framing.

- Time — Half-day of careful interpretation.

# Week 3 (August 15-21): Begin drafting

## Task 3.1 — Methods section first

- Why — Methods is the most stable section regardless of result direction. Get it on paper while the implementation details are fresh.

- How — Use scaffold Sections 5, 6, 13 as the skeleton. Translate each scaffold subsection into prose. Cite from the Mendeley library via Mendeley Cite. Include: data window and provenance; pre-processing decisions (with reasons); the barometric/hydrological decomposition; the three models and their parameterization; the four-part evaluation protocol; the transfer experiment specification.

- Output — Draft methods chapter section, ~3000-5000 words.

- Time — 3-4 days.

## Task 3.2 — Results section skeleton

- How — One paragraph per result, with the table or plot embedded. Sections: (i) calibration-site results — barometric R², Eryilmaz replication, signal characterization, three-detector outputs on Kerkrade, evaluation protocol outcomes. (ii) transfer experiment — per-site outcomes, baseline comparison, cross-detector agreement at transfer sites. Don't draft the interpretation yet; just state the numbers and what they show.

- Output — Draft results section, ~2000-3000 words.

- Time — 2-3 days.

# Week 4 (August 22-31): Polish, integrate, plan autumn

## Task 4.1 — Integrate groundwater data if received

- Why — If Jean Hacking / Rene Mols sent data during July or August, integrate it now. Re-phrase the proxy mechanism claim throughout the draft.

- How — Correlate groundwater level with the barometric residual and with the Kalman state. Both should show coherent structure if the proxy chain is real. Update Section 4 of the chapter: "observed in conjunction with" replaces "consistent with" where the data supports it.

- Output — Script 12_groundwater_integration.py. Revised methods/results draft.

- Time — 1-2 days.

## Task 4.2 — Build the figure set

- How — Final versions of: (i) study area map; (ii) example data window showing CO2, weather, discharge; (iii) barometric regression fit; (iv) ROC for Eryilmaz replication; (v) anomaly score time series for each detector; (vi) cross-detector agreement matrix; (vii) transfer-site results table or heatmap; (viii) baseline comparison. Each figure as a publication-quality PNG/PDF. Saved to results/figures/.

- Time — 2 days.

## Task 4.3 — End-of-summer review with supervisor

- Why — Three months of pushing is a natural pause. Surface the result direction, the methodological choices made, and any framing adjustments needed for autumn writing.

- How — Prepare a 1-page summary: data acquired, methods run, headline results, open questions for autumn. Discuss.

- Output — Summary doc. Notes from supervisor meeting in docs/.

- Time — Half-day prep + meeting.

## Task 4.4 — Plan the autumn work

- What remains after summer — Typically: full discussion section, full UQ analysis, robustness checks (sensitivity to thresholds, seasonality treatment, removed-features ablations), introduction and literature review polishing, citation cleanup, target-journal selection, response to supervisor feedback.

- Output — An autumn-plan.md outlining what's left and a rough month-by-month schedule for September-December.

- Time — Half-day.

# End-of-summer review

- [ ] Transfer experiment run at all selected sites.

- [ ] Results analyzed honestly against baselines.

- [ ] Methods section drafted (~3000-5000 words).

- [ ] Results section drafted (~2000-3000 words).

- [ ] Groundwater integrated if data received; proxy claim refined accordingly.

- [ ] Full figure set in publication-ready form.

- [ ] Supervisor meeting held; framing adjustments noted.

- [ ] Autumn plan written.

Honest framing for autumn The chapter at the end of August will NOT be done. It will have methods + results in defensible form, with discussion and introduction still to write. That's the right state — the discussion can be written once you've seen the results and discussed them with your supervisor. Trying to draft a discussion before this point is premature.