July 2026 — How-To

Month 2: Modelling and ensemble

Goal for the month: fit all three candidate models on the Kerkrade data; build the evaluation protocol; compute cross-detector agreement; complete the transfer-site dataset acquisition; pre-register the transfer experiment specification before any transfer-site results are inspected.

# Prerequisites from June

- Cleaned, time-aligned IoT + weather + discharge data in data/interim/.

- Soft-label event catalogue (events.csv).

- Residual-after-barometric series saved (co2-residual-barometric.csv).

- Eryilmaz replication confirmed (or framing adjusted).

- Initial residual-signal characterization done.

# Week 1 (July 1-7): SARIMAX

## Task 1.1 — Pre-processing for SARIMAX

- Why — ARIMA-family models assume stationarity. Need to check and transform.

- How — ADF test (Dickey-Fuller): null is unit root, want to reject. KPSS test: null is stationarity, want to fail to reject. Apply both to CO2 and to the barometric residual. If non-stationary, difference. Box-Cox transform to stabilize variance if CO2 is heavy-tailed (Viefhues found skew 4.02 in the before period).

- Output — Script 05_sarimax.py section 1. Documented decisions in decisions log.

- Time — Half-day.

## Task 1.2 — Order selection

- How — statsmodels.tsa.SARIMAX. Grid-search (p,d,q)(P,D,Q,s) over a small range. Optimize on AIC and BIC. With 17 months of hourly data and ~1.4 annual cycles, the seasonal terms will be weakly identified; use s=24 (daily) and s=168 (weekly) more confidently than s=8760 (annual).

- Output — Selected model orders documented. Table of AIC/BIC for candidate orders.

- Time — Half-day (statsmodels grid-search is slow on hourly data — leave it running).

## Task 1.3 — Fit and extract residuals

- How — Fit SARIMAX with exogenous regressors: weather (Visualcrossing + KNMI), pressure tendency features. Extract one-step-ahead residuals. These are the chapter's primary anomaly score for the SARIMAX family.

- Output — Fitted model artifact in results/models/sarimax.pkl. Residual time series in data/processed/sarimax-residuals.csv. Diagnostic plots: residual ACF, Ljung-Box test, Q-Q plot.

- Time — Half-day.

## Task 1.4 — Anomaly scoring from residuals

- How — Define anomaly = |residual| > threshold (3σ; or use a robust threshold like MAD-based). Save binary anomaly series.

- Output — data/processed/sarimax-anomalies.csv.

- Time — 1-2 hours.

# Week 2 (July 8-14): Kalman filter

## Task 2.1 — Specify state-space model

- Why — The chapter uses the Kalman filter for innovations-based anomaly detection, not for state estimation. State the model and defend the choice in the methods chapter.

- How — Simplest defensible specification: local-level model (state = current CO2 level, observation = CO2 + noise). Then add exogenous covariates as observation-equation regressors (weather + pressure tendency). Use filterpy or pykalman.

- Output — Script 06_kalman.py. State-space spec documented in decisions log.

- Time — Half-day.

## Task 2.2 — Tune covariances

- How — Process noise Q and observation noise R have to be set. Either: (i) MLE on Q, R via the EM algorithm (pykalman supports this); (ii) hand-tune on a held-out window. Document choice.

- Output — Tuned filter parameters. Innovation series saved.

- Time — Half-day.

## Task 2.3 — Innovations as anomaly score

- How — Standardize innovations by their estimated covariance (this is the Mahalanobis distance equivalent). Threshold to get binary anomalies.

- Output — data/processed/kalman-innovations.csv and kalman-anomalies.csv.

- Time — 1-2 hours.

## Task 2.4 — Sanity check against SARIMAX

- How — Plot SARIMAX residuals and Kalman innovations on the same axes for a few example windows. They should broadly agree on "unusual" periods. Disagreement is informative, not necessarily wrong.

- Time — 1 hour.

# Week 3 (July 15-21): Isolation Forest and ensemble agreement

## Task 3.1 — Isolation Forest on the multivariate stream

- How — sklearn IsolationForest on the full feature set (CO2, temp, humidity, pressure, PM, deltas, residual-from-barometric). Contamination parameter: start at 0.05, sensitivity-test. Use n_estimators=200, max_features=0.8.

- Output — Script 07_isolation_forest.py. Anomaly scores and binary flags in data/processed/iforest-{scores,anomalies}.csv.

- Time — Half-day.

## Task 3.2 — Cross-detector agreement

- Why — Section 6.3 / 5.2 of the scaffold relies on three-model triangulation. Compute the agreement explicitly.

- How — For each time index, compute a 3-element vector of anomaly flags (SARIMAX, Kalman, IF). Tabulate: how often do 1, 2, or 3 detectors agree? Compute pairwise Jaccard or Cohen's kappa between detector pairs. Identify windows where all 3 agree and inspect.

- Output — Script 08_ensemble_agreement.py. Agreement matrix table. Plot of CO2 with all-3-agree windows highlighted.

- Time — Half-day.

## Task 3.3 — Synthetic anomaly injection setup

- Why — Wu & Keogh 2023's critique requires a defensible alternative to label-dependent evaluation. Synthetic injection (GenIAS, CutAddPaste, NCAD) is part of that defense.

- How — Implement one or two injection templates: (i) CutAddPaste — cut a segment, paste at another location (Wang et al. 2024); (ii) Gaussian noise burst — inject a magnitude-controlled perturbation at known timestamps. Run all three detectors on the injected series and check whether they catch the injected anomalies.

- Output — Script 09_synthetic_injection.py. Detection rate per injection type per detector.

- Time — 1 day.

# Week 4 (July 22-31): Evaluation protocol + transfer prep

## Task 4.1 — Run the four-part evaluation protocol on Kerkrade

- Why — This is the chapter's defended evaluation regime. Documented in scaffold Section 5.2.

- How — (i) Anomaly-rate baselines: for each soft-labelled event in events.csv, count anomaly flags in the antecedent window vs. a matched control window. Permutation test for significance. (ii) Goswami tsadams: implement the unsupervised model-selection surrogate (see paper). Use it to rank SARIMAX/Kalman/IF without labels. (iii) Synthetic injection: already done. (iv) Cross-detector agreement: already done.

- All splits use time-aware schemes — Blocked, rolling-origin, or forward-chaining — never random k-fold. Eryilmaz (2025) used random 5-fold CV, which is methodologically suspect for autocorrelated time series; this chapter disavows it explicitly. Suggested default: rolling-origin with 30-day training windows and 7-day evaluation windows, applied uniformly across SARIMAX, Kalman, and Isolation Forest evaluation. Document chosen scheme and parameters in the decisions log; examiners will probe this.

- Output — Script 10_evaluation.py. Results table summarizing all four protocols. Written interpretation in docs/. CV scheme and parameters in decisions log.

- Time — 2-3 days.

## Task 4.2 — Acquire SMAP soil moisture for baseline comparison

- Why — Section 13.5 of the scaffold names SMAP as a baseline to beat. Pull it now.

- How — NASA Earthdata: SMAP L3 daily, ~9 km resolution. Subset to the Maas basin extent. Re-grid to nearest station locations (Kerkrade + transfer sites).

- Output — data/raw/smap/. Loader and re-gridder in io_data.py.

- Time — Half-day.

## Task 4.3 — Compute API baseline

- How — Antecedent Precipitation Index = sum of decayed past rainfall. Simplest form: API_t = sum_{k=1..N} k^(-d) * P_{t-k}. Use d=0.85 and N=14 days as standard. Compute at Kerkrade and at each transfer site.

- Output — data/processed/api.csv per site.

- Time — 1-2 hours.

## Task 4.4 — Continue transfer-site acquisition

- How — After RIVM (done in June), acquire IRCEL-CELINE (Belgium) and LANUV NRW (Germany). Same hourly schema.

- Output — data/raw/transfer/{ircel,lanuv}/.

- Time — 1-2 days (varies by API friendliness).

## Task 4.5 — PRE-REGISTER the transfer experiment

- Why — Section 13.6 of the scaffold commits to this. It's a methodological safeguard against post-hoc selection.

- How — Write docs/transfer-experiment-preregistration.md. Specify: (a) the selected transfer sites with reasons; (b) the model training procedure at Kerkrade; (c) the deployment procedure at each transfer site; (d) the success criterion (e.g. "transfer model anomaly rate during ≥90th-percentile discharge windows is significantly higher than during background"); (e) the baselines to beat (API, SMAP); (f) the statistical test. Do this BEFORE inspecting transfer-site model outputs.

- Output — Pre-registration doc committed to git (so the timestamp is verifiable).

- Time — Half-day.

# End-of-July review

- [ ] SARIMAX, Kalman, Isolation Forest all fitted with residuals/innovations/scores extracted.

- [ ] Cross-detector agreement computed.

- [ ] Synthetic injection pipeline working.

- [ ] Four-part evaluation protocol run on Kerkrade.

- [ ] SMAP and API baselines computed.

- [ ] At least 3 transfer sites ingested.

- [ ] Transfer experiment pre-registered.

- [ ] If groundwater data arrived, integrate it and re-phrase the proxy mechanism in decisions log from "consistent with" to "observed in conjunction with".